## Tasks
CITY101 — TASK TRACKER (A02 Crit: Mon 2 Mar 1pm)
✅ Done: 25 ¦ 🔧 In Progress: 0 ¦ ⬜ To Do: 27 ¦ 🔴 Blocked: 0
# | Category | Task | Owner | Priority | Status | Deadline | Depends On | Source | Notes
🔴 TONIGHT — Critical Path (1 Mar night)
1 | Data — Temporal | First/last train per station (49 stations, transport.opendata.ch) | Henna | 🔴 P1 Critical | ✅ Done | 1 Mar night | — | Team Handoff S1 → S2 overlap | Andrea completed in S9. Henna: DON'T redo. Use city101_first_last_trains.csv
2 | Data — Cost | GA cost map: SBB pricing for 35 OD pairs × 3 ticket types | Andrea | 🔴 P1 Critical | ✅ Done | 1 Mar night | — | Team Handoff S1 | Completed in S10. CHF 20 budget = 41km city.
3 | Data — Cross-ref | Classmate data cross-reference: count features within 500m of 49 stations | Andrea | 🔴 P1 Critical | ✅ Done | 1 Mar night | — | Team Handoff S1 | 2,093 points from 33 datasets. Shannon diversity computed.
4 | Data — Night | 24h venue scan: cafés/restaurants open past midnight | Henna | 🟡 P2 Important | ✅ Done | 1 Mar night | — | Team Handoff S1 | Google Places hours filter along corridor
5 | Data — Night | Noctambus / night bus routes and coverage | Henna | 🟡 P2 Important | ✅ Done | 1 Mar night | — | Handoff 23-02 S2 | Alternative network when trains stop
6 | Data — Zurich | Zurich minimal comparison: 10–12 S-Bahn stations | Andrea | 🟡 P2 Important | ✅ Done | 1 Mar night | — | Team Handoff S1 → S2 | 12 S8 stations completed, 15 structural metrics
🟡 MONDAY MORNING — Curation & Export (2 Mar)
7 | Maps — Export | Review 7 existing QGIS layouts, verify labels/legibility | Andrea | 🔴 P1 Critical | ⬜ To Do | 2 Mar AM | — | Team Handoff S2 | CITY101_WORKING.qgz, 50+ layers
8 | Maps — Export | Load new layers: temporal WCI, modal diversity, GA cost, break points | Andrea | 🔴 P1 Critical | ⬜ To Do | 2 Mar AM | GA cost ✅ | Team Handoff S2
9 | Maps — Export | Export strongest 3–5 maps as print-ready PDFs | Andrea | 🔴 P1 Critical | ⬜ To Do | 2 Mar AM | Layouts reviewed | Team Handoff S2 | A1 landscape
10 | Maps — New | MAP8: GA Cost Gradient (49 stations colored by price from Geneva) | Andrea | 🟡 P2 Important | ⬜ To Do | 2 Mar AM | GA cost data ✅ | Team Handoff S2
11 | Maps — New | MAP9: Shannon Diversity (stations by Shannon, sized by richness) | Andrea | 🟡 P2 Important | ⬜ To Do | 2 Mar AM | Crossref ✅ | Team Handoff S2
12 | Maps — New | MAP10: Temporal Triptych (3 snapshots: 7am / 1pm / 11pm) | Andrea | 🟡 P2 Important | ⬜ To Do | 2 Mar AM | Temporal WCI ✅ | Team Handoff S2
13 | Henna Data | Bring thermal comfort / UHI zones into QGIS as environmental layer | Henna | 🔴 P1 Critical | ⬜ To Do | 2 Mar AM | — | Team Handoff S2 | 203 zones + 33 comfort points — ONLY Henna has this
14 | Henna Data | Bring cold air drainage layer (nighttime environmental) | Henna | 🟡 P2 Important | ⬜ To Do | 2 Mar AM | — | Team Handoff S2
15 | Henna Data | Bring psycho-comfort data for station quality annotation | Henna | 🟡 P2 Important | ⬜ To Do | 2 Mar AM | — | Team Handoff S2
16 | Henna Data | Verify ridership data (22 stations) is integrated | Henna | 🟡 P2 Important | ⬜ To Do | 2 Mar AM | — | Team Handoff S2
17 | Narrative | Write narrative v2 (800–1000 words): integrate temporal + diversity + frontalier findings | Together | 🔴 P1 Critical | ⬜ To Do | 2 Mar AM | — | Team Handoff S2 | Current draft: 731 words in deliverables/A02_NARRATIVE_DRAFT.md
18 | Narrative | Add Henna's night/environmental paragraph to narrative | Henna | 🔴 P1 Critical | ⬜ To Do | 2 Mar AM | UHI data loaded | Team Handoff S2 | Is the Lavaux Fracture a failure or a refuge?
19 | Viz — Interactive | Build Temporal WCI Pulse (HTML, time slider, 7 slots) | Andrea | 🟡 P2 Important | ✅ Done | 2 Mar AM | Temporal WCI ✅ | Team Handoff S2 | Spec in VIZ_SPEC_CLAUDE_CODE.md
20 | Viz — Interactive | Build GA Cost Curve (HTML, budget slider) | Andrea | 🟡 P2 Important | ✅ Done | 2 Mar AM | GA cost ✅ | Team Handoff S2
21 | Presentation | Decide final map selection: 3–5 ARGUMENT maps + EVIDENCE maps | Together | 🔴 P1 Critical | ⬜ To Do | 2 Mar pre-crit | Maps exported | Team Handoff S2
22 | Presentation | Identify 3–5 intervention sites for week 2 point clouds | Together | 🔴 P1 Critical | ⬜ To Do | 2 Mar pre-crit | Break points ✅ | Team Handoff S2 | Candidates: Bussigny, Lancy-Bachet, Aigle, Cully, Rivaz, Vernier-Blandonnet, Coppet
23 | Presentation | Write/refine 2-minute opening pitch | Together | 🔴 P1 Critical | ⬜ To Do | 2 Mar pre-crit | Narrative v2 | Team Handoff S2 | Draft exists — needs temporal + diversity findings
24 | Upload | Upload all files to team Drive | Together | 🔴 P1 Critical | ⬜ To Do | 2 Mar pre-crit | All above | Team Handoff S2 | Priority files listed in handoff
✅ COMPLETED — Andrea's Sessions (24 Feb – 2 Mar)
25 | Data — Transit | Service frequency v2 (49 stations, trains/hr) | Andrea | — | ✅ Done | 28 Feb | — | Handoff S1 | 42× variation. Bug fix: API limit=30 had flattened data.
26 | Data — Transit | SBB Ridership (174 stations, daily passengers, commuter index) | Andrea | — | ✅ Done | 28 Feb | — | Handoff S1 | CI classifies station character
27 | Analysis | Break Point Analysis (49 stations, 5 break dimensions) | Andrea | — | ✅ Done | 1 Mar S6 | — | Team Handoff S1 | Only 11/49 continuous. The archipelago.
28 | Analysis | Journey Workability (618 connections, 35 OD pairs × 3 slots) | Andrea | — | ✅ Done | 1 Mar S6 | — | Team Handoff S1 | 85% not workable. Two corridors on same tracks.
29 | Analysis | WCI Computation (49 segments, 5 components) | Andrea | — | ✅ Done | 1 Mar S3 | — | Team Handoff S1 | 0.0003 to 0.6431 range
30 | Data — Reviews | Station ratings + reviews (37 stations, 71 reviews) | Andrea | — | ✅ Done | 1 Mar S6 | — | Team Handoff S1 | Zero 'work_friendly' mentions
31 | Research | Rail history 1855–2025 + ghost stations | Andrea | — | ✅ Done | 1 Mar S4 | — | Team Handoff S1 | Peak rail was 1911. 6 ghost stations.
32 | Viz | Rail history interactive HTML (Leaflet.js timeline) | Andrea | — | ✅ Done | 1 Mar S5 | — | Team Handoff S1 | rail_history_v3.html — 170 years, 18 lines
33 | Data — Federal | 14 WMS layers from geo.admin.ch (noise, EV, electricity) | Andrea | — | ✅ Done | 1 Mar S2 | — | Team Handoff S1 | National coverage incl. Zurich — free comparison
34 | Data — Mobility | Shared mobility (2,062 stations, 8 providers) | Andrea | — | ✅ Done | 1 Mar S2 | — | Team Handoff S1 | Geneva-heavy, Riviera absent
35 | Analysis | Temporal WCI (49 stations × 7 time slots) | Andrea | — | ✅ Done | 1 Mar S9 | — | Team Handoff S2 | Archipelago is structural not temporal: 14→13 stations
36 | Research | Diversity research (4 indices, Pearson correlations) | Andrea | — | ✅ Done | 1 Mar S8 | — | Team Handoff S2 | r=0.63–0.71 convergence. Shannon 1.0 threshold.
37 | Research | Frontalier research (160k ghost citizens) | Andrea | — | ✅ Done | 1 Mar S8 | — | Team Handoff S2 | Larger than Lausanne, invisible in metrics
38 | Data | Opendata.swiss trawl (50+ federal datasets scored) | Andrea | — | ✅ Done | 1 Mar S2 | — | Team Handoff S1 | opendata_trawl_categorized.md
⚪ WEEK 2 + FUTURE — Parked Items
39 | A02 Week 2 | Point Cloud Sections for high-potential sites (swissSURFACE3D) | Together | 🟡 P2 Important | ⬜ To Do | Week 2 | Intervention sites chosen | A02 Brief | Federal LiDAR scans. Need sites identified NOW.
40 | A02 Week 2 | Networked intervention strategy (3–5 sites) | Together | 🟡 P2 Important | ⬜ To Do | Week 2 | Sites chosen | A02 Brief | System that adapts to different contexts
41 | Research | GA Hypothesis full research (penetration data, behavioral segmentation) | Either | ⚪ Parked | ⬜ To Do | Future | — | TODO 4 Points | Research-heavy. Parked for now.
42 | Data | viageo.ch commune data (parking meters, benches, cycling infra) | Either | ⚪ Parked | ⬜ To Do | Future | — | Team Handoff S1 | Dwell time pricing = city's implicit program
43 | Data | Tunnel locations from OSM (cell signal dead zones on train) | Either | ⚪ Parked | ⬜ To Do | Future | — | TODO 4 Points | Completes on-train workability picture
44 | Data | View quality per segment (lake visibility from stations) | Either | ⚪ Parked | ⬜ To Do | Future | — | Team Handoff S1 | Station + lake view + bench + WiFi = premium node
45 | Data | Public bench locations near stations (mobilier urbain) | Either | ⚪ Parked | ⬜ To Do | Future | — | Team Handoff S1 | Most basic workspace infrastructure
46 | Research | Loophole economy (CFF land zoning, Coop Pronto hours) | Either | ⚪ Parked | ⬜ To Do | Future | — | Handoff 23-02 S2 | Legal geography of night commerce
47 | Viz | Diversity Dashboard (HTML, multi-panel scatter + maps) | Andrea | 🟢 P3 Nice-to-have | ✅ Done | Future | — | Team Handoff S2
48 | Viz | Station Explorer (HTML, 49 stations × 12 dimensions, radar charts) | Andrea | 🟢 P3 Nice-to-have | ✅ Done | Future | — | Team Handoff S2
49 | Viz | Journey Workability heatmap (HTML, OD matrix) | Andrea | 🟢 P3 Nice-to-have | ✅ Done | Future | — | Team Handoff S2 | 618 connections too dense for print
50 | Viz | Narrative Scrollytelling (HTML, full argument) | Andrea | ⚪ Parked | ⬜ To Do | Future | — | Team Handoff S2 | Portfolio piece, only if time
51 | Midterm | Rhino MCP modeling for 3 intervention sites | Together | 🟡 P2 Important | ⬜ To Do | Midterm | Sites chosen | Handoff 23-02 S2 | Adaptive rail-mounted module
52 | Midterm | Full Zurich WCI replication | Either | ⚪ Parked | ⬜ To Do | Midterm | — | Team Handoff S1

## Data Inventory
DATA INVENTORY — All Available Datasets
Dataset | File | Rows | Key Columns | Source | Date | Status | Used In
Core Corridor Datasets
EV Charging MERGED | city101_ev_charging_MERGED.csv | 194 | lat, lon, operator, power | OSM + Google Places | 17 Feb | ✅ | WCI, Maps
EV Charging ENRICHED v3 | city101_ev_charging_ENRICHED_v3.csv | 194 | 53 cols: DIEMO + distances + context | DIEMO + OSM + Google | 24 Feb | ✅ | Analysis
EV Charging REVIEWS | city101_ev_charging_REVIEWS.csv | 109 | Sentiment-tagged reviews | Google Places | 24 Feb | ✅ | Narrative
EV Charging CROSSREF | city101_ev_charging_CROSSREF.csv | 194 | +transit, noise, grocery proximity | Multi-source | 28 Feb | ✅ | WCI
WiFi MERGED v2 | city101_wifi_MERGEDv_2.csv | 81 | Quality scores, clusters | OSM + Google | 24 Feb | ✅ | WCI
Remote Work Places | city101_remote_work_places.csv | 68 | Google place_ids, types | Google Places | 28 Feb | ✅ | WCI
Remote Work REVIEWS | city101_remote_work_REVIEWS.csv | 109 | Work-relevance tagged | Google Places | 28 Feb | ✅ | Narrative
Remote Work HOURS | city101_remote_work_HOURS.csv | 63 | Opening hours, 14 are 24h | Google Places | 28 Feb | ✅ | WCI temporal
Remote Work CROSSREF | city101_remote_work_CROSSREF.csv | 68 | 31 cols, infrastructure proximity | Multi-source | 1 Mar | ✅ | WCI
Transit & Mobility
Service Frequency v2 | city101_service_frequency_v2.csv | 49 | trains/hr, IC/IR vs regional | transport.opendata.ch | 28 Feb | ✅ | WCI
SBB Ridership | city101_ridership_sbb.csv | 174 | Daily passengers, commuter index | transport.opendata.ch | 28 Feb | ✅ | Break points
Shared Mobility | city101_shared_mobility.csv | 2,062 | E-bikes, scooters, carshare, provider | sharedmobility.ch | 1 Mar | ✅ | WCI
First/Last Trains | city101_first_last_trains.csv | 49 | Weekday+weekend, service windows | transport.opendata.ch | 1 Mar | ✅ | Temporal
Temporal Frequency | city101_temporal_frequency.csv | 49 | 49 stations × 7 time slots | transport.opendata.ch | 1 Mar | ✅ | TWCI
Analysis Outputs
WCI Corridor Segments | city101_corridor_segments_WCI.csv | 49 | WCI 5-component score | Computed | 1 Mar | ✅ | Hero map
Temporal WCI | city101_temporal_WCI.csv | 49 | WCI per time slot | Computed | 1 Mar | ✅ | Temporal map
Break Points | city101_break_points.csv | 49 | 5 break dimensions, severity | Computed | 1 Mar | ✅ | Break map
Journey Workability | city101_journey_workability.csv | 618 | 35 OD × 3 slots, classification | transport.opendata.ch | 1 Mar | ✅ | Two corridors
Journey Work Summary | city101_journey_workability_summary.csv | 35 | OD pair aggregates | Computed | 1 Mar | ✅
Train Workability | city101_train_workability.csv | 49 | IC/IR vs R/S ratio per station | Computed | 1 Mar | ✅
GA Cost Corridor | ga_cost_corridor.csv | 49 | Price by ticket type per station | Estimated (distance-based) | 1 Mar | ✅ | GA map
Station Crossref Classmates | city101_station_crossref_classmates.csv | 49 | 46 cols: 33 datasets × proximity | Classmate data | 1 Mar | ✅ | Diversity
Modal Diversity | city101_modal_diversity.csv | 49 | Shannon per station, 11 modes | Computed | 1 Mar | ✅ | Diversity
Reviews & Ratings
Station Ratings | city101_station_ratings.csv | 37 | M2, M1, CGN, LEx with Google ratings | Google Places | 1 Mar | ✅ | Quality map
Station REVIEWS | city101_station_REVIEWS.csv | 71 | Tagged by theme | Google Places | 1 Mar | ✅ | Dark data
National / Federal
Swiss Charging Stats | swiss_charging_keyfigures_monthly.csv | 63 | Monthly national benchmark 2020–26 | opendata.swiss | 1 Mar | ✅ | Context
Cell Towers | city101_cell_towers.csv | 3,218 | 3G/4G/5G, operator, location | BAKOM | 24 Feb | ✅ | Connectivity
International Anchors | city101_international_anchors.csv | 15 | CERN, UN, IOC, etc. | Manual | 24 Feb | ✅ | Context
14 WMS Layers | (loaded in QGIS) | — | Noise, EV 2035, electricity demand | geo.admin.ch | 1 Mar | ✅ | Zurich comp
Henna's Data (to integrate)
UHI High Peak | hennarafik-UHIhighpeakheatislands.csv | 40 | Heat island zones | Own research | Feb | 🟡 | Environmental
UHI Medium | hennarafik-UHImediumtransitionzones.csv | 54 | Transition zones | Own research | Feb | 🟡 | Environmental
UHI Low Cool | hennarafik-UHIlowcoolzones.csv | 109 | Cool zones | Own research | Feb | 🟡 | Environmental
Thermal Comfort | hennarafik-thermalcomfort.csv | 33 | Comfort points | Own research | Feb | 🟡 | Environmental
Station Ridership | (Henna's ridership data) | 22 | Daily + workday averages | Own research | Feb | 🟡 | Verify integrated
Zurich Comparison
Zurich S8 Comparison | zurich_sbahn_comparison.csv | 12 | Frequency, workspace, WCI analog | ZVV + Google | 1 Mar | ✅ | Comparison map
Not Yet Fetched
24h Venues | — | — | Past-midnight cafés/restaurants | Google Places | — | ⬜ | Night dimension
Noctambus Routes | — | — | Night bus network | TL / tpg | — | ⬜ | Gap hours
viageo.ch Commune Data | — | — | Parking meters, benches, cycling | viageo.ch | — | ⬜ | Parked
Tunnel Locations | — | — | Cell signal dead zones | OSM | — | ⬜ | Parked

## Map Plan
MAP & VISUALIZATION PLAN — What to Print, What to Show Live
Map ID | Title | Type | Data Source | Argument | Format | Status | Owner
🗺️ ARGUMENT MAPS — Print Large, Present First
MAP A | The Archipelago (WCI hero) | Print A1 | corridor_segments_WCI.csv | The linear city doesn't exist — 11 nodes, 3 gaps dimensioned | PDF A1 | ⬜ To Do | Andrea
MAP B | Two Corridors / Journey Workability | Print A1 | journey_workability.csv | IC vs S-Bahn = same tracks, two cities | PDF A1 | ⬜ To Do | Andrea
MAP C | Temporal Corridor (3 timestamps) | Print A1 | temporal_WCI.csv | 8am / 8pm / 2am — the line dying at night | PDF A1 | ⬜ To Do | Andrea
📊 EVIDENCE MAPS — Print Smaller or Screen
MAP D | Lavaux Fracture Zoom | Print A3 | WCI + frequency + workspaces | The wound up close — failure or refuge? | PDF A3 | ⬜ To Do | Andrea
MAP E | Break Point Classification | Print A3 | city101_break_points.csv | 49 stations by severity, paradox stations labeled | PDF A3 | ⬜ To Do | Andrea
MAP F | Transit Backbone | Print A3 | service_frequency_v2 + ridership | 42× variation, ridership bubbles | PDF A3 | ⬜ To Do | Andrea
MAP G | Remote Work Infrastructure | Print A3 | remote_work_CROSSREF + wifi | 68 workspaces + hours (open/closed/24h) | PDF A3 | ⬜ To Do | Andrea
MAP H | Zurich Comparison | Print A3 | zurich_sbahn_comparison.csv | Radial vs linear, same metrics | PDF A3 | ⬜ To Do | Andrea
MAP I | Shared Mobility Coverage | Print A3 | city101_shared_mobility.csv | Geneva-heavy, Riviera absent | PDF A3 | ⬜ To Do | Andrea
MAP8 | GA Cost Gradient | Print A3 | ga_cost_corridor.csv | Your city depends on your wallet | PDF A3 | ⬜ To Do | Andrea
MAP9 | Shannon Diversity | Print A3 | station_crossref_classmates.csv | Diversity = completeness (Shannon threshold) | PDF A3 | ⬜ To Do | Andrea
MAP10 | Temporal Triptych | Print A3 | temporal_WCI.csv | 3 snapshots: 7am / 1pm / 11pm — doesn't pulse | PDF A3 | ⬜ To Do | Andrea
💻 INTERACTIVE VISUALIZATIONS — Show Live at Crit
VIZ 1 | Temporal WCI Pulse | HTML | temporal_WCI.csv | Time slider — counter barely moves (14→13) | Leaflet+D3 | ✅ Done | Andrea | ⬜ To Do
VIZ 2 | GA Cost Curve | HTML | ga_cost_corridor.csv | Budget slider → 'your city ends here' | D3 | ✅ Done | Andrea
VIZ 3 | Diversity Dashboard | HTML | crossref + modal_diversity | Multi-panel scatter + correlation bars + mini-maps | D3 | ✅ Done | Andrea
VIZ 4 | Zurich Comparison | HTML | zurich_sbahn_comparison.csv | Two geographies side-by-side, same color scale | Leaflet | ✅ Done | Andrea
VIZ 5 | Station Explorer | HTML | crossref + temporal + GA | 49 stations × 12 dims, radar charts, compare | D3 | ✅ Done | Andrea
EXISTING | Rail History Timeline | HTML | rail_history_v3.html | 170 years, 18 lines, 6 ghost stations, play/pause | Leaflet | ✅ Done | Andrea
🖥️ LIVE QGIS — Exploration During Crit
QGIS | 50-layer project | Live | CITY101_WORKING.qgz | Live querying, toggle layers, zoom to details | QGIS | ✅ Loaded | Andrea

## Key Findings
KEY FINDINGS — Crit Cheat Sheet
Finding | Detail | Use In Crit
The Archipelago | Only 11/49 stations (22%) maintain full working continuity. 3 structural gaps: Nyon→Gland 19.3km, Gland→Morges 20km, Lavaux Fracture 17.5km | LEAD finding. Hero map.
Two Corridors on Same Tracks | IC = 46min office (WiFi, tables, quiet car). S-Bahn = 90-sec interruptions, can't open laptop. 85% of connections NOT workable. | Second punch. Journey workability map.
42× Frequency Variation | Lausanne 28.5 tr/hr (2-min wait) → Bossière 2.0 (37-min) → St-Saphorin 0.0 | Transit backbone map. Scale of inequality.
2,000× WCI Variation | Geneva 0.6431 → St-Saphorin 0.0003 | Quantifies the archipelago.
Frequency-Amenity Paradox | Bussigny 9 tr/hr, Lancy-Bachet 12.5, Aigle 16.5 = great transit, ZERO workspaces. Train delivers you to a void. | Intervention site rationale.
Doesn't Pulse | 14 stations workable at peak, 13 at 11pm. The archipelago is structural, not temporal. | Temporal map. Counters 'just a rush hour problem.'
CHF 20 = 41km City | Full-price budget reaches St-Prex, 12km short of Lausanne. GA daily = CHF 10.58 = 101km. Short-hop penalty 6×. | GA cost map. Equity argument.
160,000 Ghost Citizens | Frontaliers larger than Lausanne, invisible in every metric, can't buy GA. | Frontalier paragraph in narrative.
Diversity Convergence | 4 independent indices (religious, modal, economic, culinary) all converge: r = 0.63–0.71. Shannon 1.0 threshold: below = 8.8 avg richness, above = 70.5 (8× jump). | Diversity map. Comtesse validation.
Lavaux = Systemic Collapse | Not just a transit gap — economic, modal, demographic diversity all collapse simultaneously. | Fracture zoom map.
Nobody Reviews for Work | Zero 'work_friendly' in 71 station reviews. Station-as-workplace is invisible. | Dark data argument.
Peak Rail Was 1911 | More connectivity 115 years ago. 6 ghost stations killed by Rail 2000 in 2004. Clarens-Chailly tramway demolished 1955. | Rail history viz. Contraction narrative.
Zurich Comparison | Same country, same operator. Radial compresses variation (12×), linear amplifies (42×). Worst Zurich lakeside: 2 tr/hr. Worst City101: 0. | Zurich comparison map.
Henna: Thermal + Night | Is Lavaux Fracture the worst for work AND best for rest? UHI + cold air drainage as environmental quality layer. | Environmental paragraph in narrative.